## Instructions
Instructions | Enter your team name as specified in the cell below. When doing cross-team acceptance testing, enter the name for the testing group. Fill-in the Test Plan worksheet with all the remaining User Stories in your Product Backlog. Since Product acceptance is from the perspective of the end-user, only add User Stories that pertain to the Owner or Buyer and do not include User Stories specifically for the REST API service (e.g. AS a developer...). As your user stories are refined, add the acceptance criteria for each user story. Use a separate worksheet to provide any specific test case data that the tester needs to use. As tests are performed in each sprint, indicate Pass/Fail. Note that there are separate columns for each sprint. The tester should add initials and a date in the comments column. If the test failed, the tester is required to add additional information about the failure. The status cell will color code based on the test results. The comments cell will color code when a test result exists but no information is entered. Save this test plan with a name formatted as "term-swen-261-sec-letter name", e.g. 2171-swen-261-10-a Speedy Racers.xslx. Submit this file per the instructions specified for the sprint submissions and cross-team testing.
Team Name | 2215-swen-261-06-d-jadin
Testing Team Name | fill in when doing cross-team testing

## Test Plan
User Story | Acceptance Criterion | Sprint 2 | Tester initials; date; comments (required if test failed) | Sprint 3 | Tester initials; date; comments (required if test failed)
As a buyer I should be able to manipulate my shopping cart to purchase only the items I have an interest in. | Given I have items in my shopping cart when I no longer want to buy an item then I expect to be able to remove an item from my shopping cart. | Fail
| Given whether I have items in my shopping cart or not when I want to purchase an item then I expect to be able to add an item to my shopping cart. | Fail
As a buyer I want to have my shopping cart save between sessions in order to continue editing after logging back in. | Given I log out when I am a customer, then I expect to have the same items in my shopping cart when I log back in. | Fail
As a customer I want to be able to search for a product so that I can add it to my shopping cart. | Given I search for a product in the search bar when that product is present in the inventory then I expect the results to include the product. | Pass | AV, March 14, 2022
| Given I search for a product in the search bar when that product is not present in the inventory then I expect the results to not include any products. | Pass | AV, March 14, 2022
| Given I search for a product in the search bar when there is a similar product present in the inventory then I expect the similar product to show up. | Pass | AV, March 14, 2022
As the owner I should have permission to edit the inventory to how I see fit so that I can sell the necessary items. | GIVEN I submit a request to edit the inventory WHEN products exist in the inventory THEN the system should return a list of products and a status code of 200 (OK). | Pass
| GIVEN I submit a request to edit the inventory WHEN no products exist in the inventory THEN the system should return an empty list of products and a status code of NOT_FOUND | Pass
| GIVEN I submit a request to add a product to the inventory WHEN I give the credentials to create a product, THEN the product should get added to the inventory. | Pass | AV, March 14, 2022
| GIVEN I have permission to edit the inventory WHEN I request to delete a product THEN the product should be removed. | Pass | AV, March 14, 2022
As a user I want to be able to log in from a login screen so that I may access the website. | GIVEN I enter a username WHEN my information is valid within the system THEN I should be granted permission to access the website | Pass | NL, March 14, 2022
| GIVEN I enter the username "admin" WHEN I log in, THEN I should be logged in as an admin. | Pass | NL, March 14, 2022
| GIVEN I enter a username WHEN my information is not valid within the system THEN I should get an account created and be granted permission to access the e-store. | Pass